## Sheet1
| Action Item # | Raised on | AI content | AI assigned to | Target closure date | Action done | AI status | Remarks
1 | AI 2019-01 | 2019 May | MPIG to provide comments to aid the enhancement on CIP EASA-2019-05, Analysis of bonding devices in MSG-3. (AI background: CIP returned to the originator for additional work, information or justifications for re-submit in 2020. IMRBPB requested MPIG to provide comments to support the enhancement on this CIP. | MPIG |  | CIP EASA-2019-05 dismissed. | Closed | Action Item closed during IIM 2023. EASA CIP number changed in 2021 in CIP EASA-2020-05. Presented in IAM 2021 (virtual), returned to submitter for rework. Presented in IAM 2022 (virtual), returned to submitter for rework. EASA decided to dismiss the CIP in 2023.
2 | AI 2019-02 | 2019 May | EASA to create a Working Group dedicated to Bilateral discussions with FAA and TCCA. The outcome of this WG may be a new submission of the CIP by 2020. CIP EASA-2019-06, Letter of Information for projects under Bilateral Agreements. (AI background: CIP returned to the originator for additional work, information or justifications. EASA to take action to create a Working Group dedicated to Bilateral discussions with FAA and TCCA. The outcome of this WG may be a new submission of the CIP by 2020. | EASA |  | not really linked to our activity | Closed | IAM 2023
3 | AI 2019-03 | 2019 May | FAA to review IP123 and IMPS 5.9 and may come up with further proposal in 2020 on CIP FAA-2019-01, Calendar Clock Stoppage and Calendar (Time) Interval. (AI background: CIP returned to the originator for additional work, information or justifications. IMRBPB considered that the CIP’s intent is already covered by IP123 and IMPS 5.9. FAA to take action to review IP123 and IMPS 5.9 and may come up with further proposal in 2020.) | FAA |  | Following internal review, FAA confirmed no need to further investigate the issue. | Closed | IIM 2023
4 | AI 2019-04 | 2019 May | TCCA to engage CMT to harmonize the CMCC processes as per RMT.0252 Subtask 5 decision, especially on tagging of CMCC tasks, of FAA (AC 25-19A) and EASA (AMC 25-19 Appendix 3) possibly where AC 25-19A would be updated consequentially. CIP FAA-2019-02, Candidate CMR’s (CCMR) dispositioned using MSG/MRBR Tasks. (AI background: IMRBPB considered that the coverage of CCMRs by MRBR tasks was already thoroughly discussed in the pastand superseded by the direction given by the RMT.0252 Subtask 5, resulting in the 2019 IMRBPB Meeting Summary Page 8 publication of the new EASA AMC 25-19 into CS-25 Amendment 20. However, the current FAA and TCCA guidance materials are not yet in line with the guidelines agreed at RMT.0252 Subtask 5. TCCA has taken an action to bring this issue at CMT level in order to push the alignment of all the guidance materials as per RMT.0252 Subtask 5 decision. | TCCA |  | brought to CMT, CCMR removed from MSG-3 | Closed | IAM 2023
5 | AI 2019-05 | 2019 May | MPIG to propose a new CIP to update MSG-3 to the current EASA standard AMC 25-19 on CMCC process, especially on tagging of CCMR tasks. CIP FAA-2019-02, CCMR dispositioned using MSG/MRBR Tasks. | MPIG |  | Following the approval of IMRBPB IP 205. | Closed | IIM 2023
6 | AI 2019-06 | 2019 May | TCCA to raise CIP on coverage of FDR / CVR in MSG-3. | TCCA |  | Superseded by AI 2023-03 | Closed | IAM 2023
7 | AI 2019-07 | 2019 May | FAA (Seattle AEG) to find out if the FAA requirements on FDR / CVR are only applicable to MRB Report of individual, but not all, TCH. | FAA |  | Superseded by AI 2023-03 | Closed | IAM 2023
8 | AI 2019-08 | 2019 May | Retrieval of IMRBPB data such as Action Item List. | FAA |  | All IMRBPB data provided | Closed | IAM 2023
9 | AI 2019-09 | 2019 May | FAA to liaise with MPIG on the communication initiative between IMRBPB and MPIG between IMRBPB Meetings, such as CIP development and interaction between Leadership Teams of IMRBPB and MPIG. | FAA |  | Communication Procedure now available to the IMRBPB | Closed | IAM 2023
10 | AI 2019-10 | 2019 May | EASA to review IMRBPB Charter with respect to: (i) Mandatory adoption of IMPS, (ii) Approval of MSG-3 document and IMPS by IMRBPB. | EASA |  | Bullets 7. and 16. implemented into the Charter | Closed | IAM 2023
11 | AI 2020-XX-a | 2020 May | IMRBPB agreed to re-institute the Fall Regulatory Only Meeting. FAA (Bill), EASA (Raffaele and Dominique) and HKCAD (Jimmy) would take an action to amend, where necessary, the IMRBPB Charter to improve clarity on the purpose of the Fall Regulatory Only (Working Group) Meeting. MPIG had previously indicated that they supported the idea of re-instituting the Regulatory Only Meeting. | IMRBPB Leadership |  | 2021 Oct: Charter was revised and signed by member authorities after the 2021 May web meeting. | Closed | AI was not serialised during the web meeting.
12 | AI 2020-XX-b | 2020 May | IMRBPB Leadership Team would discuss and come up with target date (of January / February 2021) for the next RO meeting. | IMRBPB Leadership |  | 2021 Oct: RO meeting was held on 10th February 2021. | Closed | AI was not serialised during the web meeting.
13 | AI 2020-XX-c | 2020 May | EASA (Raffaele and Dominique) to take action to draft guidance on CIP “Preliminary” Review. | EASA |  | 2021 Oct: IMRBPB – MPIG – RMPIG Activities and Communication Procedure was issued on September 2021. (Note: the document was drafted by Raffaele, Dominque and Tony Harbottle) | Closed | AI was not serialised during the web meeting.
14 | AI 2021-XX-a | 2021 Feb | IMRBPB Leadership to arrange one or two small virtual meetings before the May meeting. | IMRBPB Leadership |  | 2021 Oct: Three CIP review task force meetings were arranged to discussed certain CIP proposed by industry. Those CIPs were eventually accepted during the 2021 May meeting. | Closed | AI was not serialised during the web meeting.
15 | AI 2021-XX-b | 2021 Feb | IMRBPB Leadership to amend Charter to reflect the new quorum after GCAA joined IMRBPB. | IMRBPB Leadership |  | 2021 Oct: Charter was revised and signed by member authorities after the 2021 May web meeting. | Closed | AI was not serialised during the web meeting.
16 | AI 2021-XX-c | 2021 Feb | IMRBPB Leadership to review the Charter on the provisioning of the Regulatory Only Meeting. If considered necessary, IMRBPB Leadership to propose amendment to the Charter. | IMRBPB Leadership |  | 2021 Oct: Charter was revised and signed by member authorities after the 2021 May web meeting. | Closed | AI was not serialised during the web meeting.
17 | AI 2021-XX-d | 2021 Feb | (e) IMRBPB leadership to establish virtual meeting with industry on the handling of the outstanding CIP. | IMRBPB Leadership |  | 2021 Oct: Three CIP review task force meetings were arranged to discussed certain CIP proposed by industry. Those CIPs were eventually accepted during the 2021 May meeting. | Closed | AI was not serialised during the web meeting.
18 | AI 2021-XX-e | 2021 Feb | (f) IMRBPB Leadership to schedule a regulatory only meeting in March 2021 to discuss the handling on the outstanding CIP. | IMRBPB Leadership |  | 2021 Oct: Three CIP review task force meetings were arranged to discussed certain CIP proposed by industry. Those CIPs were eventually accepted during the 2021 May meeting. | Closed | AI was not serialised during the web meeting.
19 | AI 2021-01 | 2021 May | MPIG Chair to identify the industry L/HIRF experts that would participate in the further refinement of the CIP EASA-2020-02 and EASA-2020-05. | MPIG |  |  | Closed
20 | AI 2021-02 | 2021 May | With the acceptance of CIP IND-2019-21 as amended as IP 192, Industry Structure WG to review the implication of the SSI definition that may potentially link to “Other Structure” in consideration with “Adverse Effect on Safety” in the framework of MSG-3 and IMPS. | MPIG (Industry Structure WG) | IAM 2024 | Action Item superseded by the new AI 2024-01. | Closed | Linked to AI 2021-13. IAM 2024 The SWG attempted to better understand what the PB intended. Several efforts were made to seek clarification w/o success. This may have been superseded w/ EASA CIP 2023-07, currently ON-HOLD following the interaction with the STR WG. The STR WG identified a roadmap with reference to the revision of the SSI definition (ref. to dedicated presentation on IAM '24 DAY 5, agenda item #8)
21 | AI 2021-03 | 2021 May | CIP IND-2020-01 to be refined based on the comments provided on 28th May 2021. CIP would be further discussed in a virtual meeting by end June 2021 / early July 2021. | MPIG (together with Gulfstream A. Chieffi) |  | CIP IND-2020-01 accepted as IP 204 (IAM 2022). | Closed | IAM 2023
22 | AI 2021-04 | 2021 May | FAA to coordinate with A4A to make available the SAE documents associated with IVHM to the IMRBPB regulatory members. | FAA |  | not possible, docs only for sale. | Closed | IAM 2023
23 | AI 2021-05 | 2021 Sep | MPIG Co-chair (Edwin Davis) to take action to discuss within MPIG and RMPIG for the possibility of providing presentation on the application of IP 180 / IP 170 in the IMRBPB December 2021 meeting . | MPIG Co-chair (Edwin Davis) | IAM 2024 | MPIG and RMPIG updated the 2021 IIM (Dec '21) where limited applications of IP 170 / IP 180 were taking place. | Closed | IAM 2024 Recorded in the IIM Dec'23 MoM
24 | AI 2021-06 | 2021 Sep | IMRBPB Chair (Bill Heliker) to take action to include the format (“hybrid” for example) of future meetings as an agenda item in the IMRBPB December 2021 meeting. | FAA (Bill Heliker) |  | Discussed in 2021 IIM where face-to-face meeting is preferred, with virtual meeting as a back-up. | Closed
25 | AI 2021-07 | 2021 Sep | IMRBPB Leadership to take action to provide four proposals on the dates of the May 2022 meeting for discussion as an agenda item during the December 2021 meeting. IMRBPB Leadership Team to work on the date proposals including ANAC, prior to the December 2021 meeting. | IMRBPB Leadership |  | 2021 Oct: 2021 Week 18 (25th to 29th April 2021). | Closed
26 | AI 2021-08 | 2021 Sep | FAA to take action to find out the status of the FAA CIP on recording device. | FAA |  | Superseded by AI 2023-03. | Closed | IAM 2023
27 | AI 2021-09 | 2021 Sep | MPIG Secretary agreed to take action to review within MPIG to re-submit IND-2020-01 (Update of MRB and CMCC Process Interface Description) in the IMRBPB December 2021 meeting. | MPIG | IAM 2024 | Action Item superseded following the approval of IP 204 "Removal of MRB and CMCC process coordination section from the MSG-3 document". | Closed | IAM 2024 IP 204 incorporated into MSG-3 Rev. 2022.2, Vol.1 and Vol.2
28 | AI 2021-10 | 2021 Sep | FAA (Bill Heliker) to take action to liaise within FAA (Todd Perry) on the status of FAA AC 25-19B. | FAA |  | Presentation provided in IAM 2022. | Closed | IAM 2023
29 | AI 2021-11 | 2021 Sep | MPIG Secretary to take action to provide a briefing paper on the problems facing by type certificate holders on MRBR approvals. This would be available for the IMRBPB December 2021 meeting. | MPIG | IIM 2024 | Action created during IMM Sept '21. Discussed during IIM Dec '21, postponed to IAM'22. MPIG position: Bill Mercier provided this overview / update, but no record of the AI closure. |  | Re-discussed during IAM 2024. Waiting for input from MPIG
30 | AI 2021-12 | 2021 Dec | MPIG Secretary to take an action item to request Boeing for a presentation on IP180 application on Boeing 787 in the May 2022 IMRBPB Annual Meeting. | MPIG | IAM 2024 | Jeff Miller (Boeing) presented this update during IAM'22. | Closed | IAM 2024 Recorded as "Appendix B" to the IAM'22 MoM. Linked to AI 2021-05
31 | AI 2021-13 | 2021 Dec | IMRBPB Leadership to take an action item to discuss with Dominique to review the 25th October 2021 email (clarifying the scope of AI 2021-02 on in-flight loss of other structure) from Kevin to decide how to address it and further communicate with MPIG if side-meeting would be required. | IMRBPB Leadership | IAM 2024 | Action Item superseded by the new AI 2024-01. | Closed | Re-discussed during IIM 2023 Linked to AI 2021-02 IAM 2024 The STR WG identified a roadmap with reference to the revision of the SSI definition (ref. to dedicated presentation on IAM '24 DAY 5, agenda item #8)
32 | AI 2022-01 | 2022 Mar | Raffaele Iovinella agreed to take an action item to contact CAA UK on the arrangement for CAA UK to participate in IMRBPB activities, initially as observer of the June 2022 IMRBPB Annual Meeting. | EASA (Raffaele Iovinella) |  | UK CAA contacted and invited to the IMRBPB. | Closed
33 | AI 2022-02 | 2022 March | Luca Tosini agreed take an action item to provide Bill, prior to the June meeting, on IMRBPB initiative such as dedicated IMRBPB AHM / IAHM Working Group and / or possible collaboration with the corresponding SAE Steering Group. Bill would then pass the info to Dr. Ravi Rajamani, and to be discussed with all during the June 2022 IMRBPB Annual Meeting. | EASA (Luca Tosini) |  | Dr Ravi contacted. | Closed | IAM 2023
34 | AI 2022-03 | 2022 March | IMRBPB Leadership agree to take an action item to discuss the need for providing training to NAA talents after the June 2022 IMRBPB Annual Meeting. | IMRBPB Leadership | IAM 2024 |  | Closed | Re-discussed during IIM 2023 IAM 2024
35 | AI 2022-04 | 2022 March | Bill Heliker agreed to take an action item (AI 2022-04) to schedule a meeting in April between IMRBPB Leadership and MPIG/RMPIG Leaderships on MSG-3 Revision / Schedule | FAA (Bill Heliker) |  | Meeting arranged on 14 April 2022. | Closed
36 | AI 2022-05 | 2022 June | IMRBPB Leadership and MPIG/RMPIG Leadership, by 2022 ILM Meeting, to discuss the preparatory work to form the MSG-4 Working Group. | IMRBPB Leadership MPIG/RMPIG Leadership |  | IMRBPB Leadership would discuss with MPIG/RMPIG Leadership on 2022 IMM (5th Oct 2022). MSG-4 WG created. | Closed | IAM 2023
37 | AI 2022-06 | 2022 June | With the removal of CMCC process from MSG-3 document, IMRBPB members and participants are kindly requested to document policy associated with their sustainment practices of legacy programs (even if they are different) regarding CCMR results realized under previous MSG-3 guidance. Each NAA is also requested to update industry routinely (e.g. quarterly) given the significant impact and confusion which currently exists for both OEMs and Operators. | IMRBPB Leadership MPIG/RMPIG Leadership | IAM 2024 | Created a survey to choose between the following 2 options: 1. to close the action without further follow-up. 2. to add a dedicated fixed slot in the future IAMs for NAAs to provide feedback when necessary. Results presented during the IAM'24. Both IMRBPB and MPIG/RMPIG voted for option 1. | Closed | IAM 2024
38 | AI 2022-07 | 2022 June | IMRBPB Leadership, with the help of TCCA IMRBPB focal who would participate in the CMT meeting, (a) to include an agenda item in the 2023 IAM on the topic of CMCC interface with ISC, and (b) the development of an CIP on updating IMPS in regard to CMCC process. | IMRBPB Leadership |  | FAA (Bill Heliker) liaised with TCCA IMRBPB focal accordingly. | Closed | IAM 2023
39 | AI 2022-08 | 2022 June | FAA (Bill Heliker) to update IMRBPB and MPIG/RMPIG on the development of the revision of FAA AC 121-22D and FAA AC 25-19. | FAA (Bill Heliker) |  | Detailed debrief provided by FAA on the status of both documents. | Closed | IIM 2023
40 | AI 2022-09 | 2022 December | Member authorities to provide comments / suggestions by 28th February 2023 on the need to revise the IMRBPB Charter on matching with the activities mentioned by the Communication Procedure. | Member authorities |  | Feedback received, no action. | Closed | IAM 2023
41 | AI 2022-10 | 2022 December | Member authorities to provide comments 60 days prior to (i.e. 9 March 2023) the May 2023 IAM on (1) IP Index Matrix, and (2) Disposition of 12 IPs that are not really IPs. (Note: On the review of the IP Index Matrix, please review the whole matrix with additional attention to (a) "RETROACTIVE" of IP 14, 96, 98, 102 & 123, (b) "ACTIVE" of IP 1, 6, 14, 98, 102, 104, 105 & 120 and "ARCHIVED" of IP 2, 4, 26, 31, 32, 38, 53, 86, 91, 106, 107 & 134 (following the approval of IP 204)) | IMRBPB Leadership & member authorities |  | Feedback received. | Closed | IAM 2023
| AI 2022-11 | 2022 December | IMRBPB Leadership to seek confirmation from MPIG / RMPIG on the identified “12 IPs that are really not IPs”. | IMRBPB Leadership |  | Feedback received. | Closed | IAM 2023
| AI 2022-12 | 2022 December | Member authorities / Industry to provide comments / suggestions by 28th February 2023 on (1) verbiage in the Communication Procedure to be enhanced in regard to the goal of preliminary discussion on CIP in the IIM, and (2) any other areas for improvement in the Communication Procedure, such as Section 3 on managing CIP that affecting both MSG-3 Vol 1 & 2. | Member authorities & MPIG / RMPIG Leadership |  | No input for improvement received within the deadline. | Closed | IIM 2023
| AI 2022-13 | 2022 December | Airbus to consider initiating an CIP on integrating the use of drone for GVI to MSG-3. | Airbus (Oliver Weiss) | IAM 2024 | CIP IND 2023-01 presented during IAM '23. | Closed | IAM 2024
| AI 2023-01 | 2023 May | to update the Charter to allow industry members to host an IAM (today just IMRBPB Members, namely the authorities) | IMRBPB Leadership Team |  | Charter updated (terms of reference, bullet 5), signed and posted on the EASA website | Closed | IIM 2023
| AI 2023-02 | 2023 May | to check within IMRBPB documents if there is any problem in having more than one Leadership Team role occupied by the same authority | IMRBPB Leadership Team |  | The same authority cannot be in chair/co-chair position. No reference to the secretary position. | Closed | IAM 2023
| AI 2023-03 | 2023 May | to develope a new regulatory CIP (TCCA) to cover the FDR/CVR issue related to AI 2019-06 and AI 2019-07. Intent: to amend MSG-3 to accommodate safety related system to produce tasks to maintain integrity of such systems (e.g. FDR/CVR, ULB and ELT) | TCCA | IAM 2024 | TCCA investigation completed, presentation provided during the IAM '24 (ref. to dedicated presentation on IAM '24 DAY 5, agenda item #10) | Closed | IAM 2024
| AI 2023-04 | 2023 May | to propose options for EASA website to keep old IPs not approved available for consultation/download | EASA (Luca Tosini) | IIM 2024 |  |  | Re-discussed during IIM 2023
| AI 2023-05 | 2023 May | at the next IMPS revision opportunity, to change "AEG" in "AED" (FAA) in the acronyms list | IMRBPB Leadership Team | IMPS Issue 03 revision approval (2025)
| AI 2023-06 | 2023 May | at the next IMPS revision opportunity, to rework IMPS Appendix 3, to make it a repository of additional supporting information/general practices. The Appendix has to be structured in sub-appendices (3.1, 3.2). The title of Appendix 3 has to be properly defined. | IMRBPB Leadership Team | IMPS Issue 03 revision approval (2025)
| AI 2023-07 | 2023 May | to investigate the possibility/implications to cover "Placards and Markings" in the MRB process making use of MSG-3 analysis | MPIG/RMPIG | IAM 2024 | Dedicated presentation provided on IAM '24 DAY 1, agenda item #4. Action closed with no further action. | Closed | IAM 2024
| AI 2023-08 | 2023 December | to discuss the need for IMRBPB consensus of regulatory proposed CIPs prior to the official submission for the Annual Meeting | IMRBPB Leadership Team | IMM March'24 | To continue with the current way of working. According to the IMRBPB Charter, the Member Authorities maintain their own independence. | Closed | IAM 2024
| AI 2023-09 | 2023 December | to discuss the IMRBPB view regarding the possible transition from MSG-3 to MSG-4 | IMRBPB Leadership Team | IMM March'24 | Agree to move forward with MSG-4 development, with conditions (ref. To AI 2024-03). | Closed | Linked to AI 2024-03 IAM 2024
| AI 2024-01 | 2024 May | EASA to present a CIP related to a new SSI definition, on the bases of the presentation "SSI Definition update-Roadmap" discussed during IAM '24. | EASA | IAM 2025 |  |  | Supersedes AI 2021-02 and AI 2021-13
| AI 2024-02 | 2024 May | To draft a new regulatory CIP, on the bases of the TCCA presentation Option 2 (ref. To AI 2023-03) | TCCA | IAM 2025 |  |  | Supersedes AI 2023-03
| AI 2024-03 | 2024 May | To complete the transition from MSG-3 to MSG-4, based on the following conditions: 1. To keep MSG-3 alive as long as needed, i.e. until we are ready to switch to MSG-4 and to discontinue MSG-3. 2. MPIG/RMPIG to clearly DEFINE what is MSG-4. 3. To assess the impact on existing fleets whose MRBR are based on MSG-3. 4. To perform a risk assessment for the transition. 5. To represent the timeline/roadmap for implementation, maybe open-ended with milestones set in-between. | MPIG/RMPIG | TBD |  |  | Supersedes AI 2023-09
| AI 2024-04 | 2024 May | With reference to the L/HIRF Assurance Plan (or equivalent validation program), each NAA to look into ist own guidance materials and available SAE standards, to identify any regulatory requirement to have an assurance plan, and to clarify who in each NAA is the process owner for the control/follow-up of it. | IMRBPB | IAM 2025 |  |  | Re-discussed during IMM 2024-02 Agreed to change the Target Closure Date from IIM 2024 to IAM 2025. Agreed to specify that the focus is on the L/HIRF Assurance Plan.
| AI 2024-05 | 2024 May | Following the approval of IP 216, to review the Applicability & Effectiveness Criteria table in MSG-3 Systems analysis: 1. to segregate "Lubrication" task from "Servicing" task. 2. to identify potential room for improvement of the current Applicability & Effectiveness guidelines. | MPIG/RMPIG | IAM 2025
| AI 2024-06 | 2024 May | To draft a new L/HIRF regulatory CIP, on the bases of the EASA presentation (ref. to dedicated presentation on IAM '24 DAY 5, agenda item #7) | EASA | IAM 2025